## Time
Task | Starting date | Finishing date | Responsible personnel
Composing of the project plan | 2017-08-28 | 2017-08-29 | PM's
Defining the scope | 2017-08-30 | 2017-08-31 | All
Identify and agree on main deliverables | 2017-08-31 | 2017-09-02 | All
Present individual WBS structures and discuss | 2017-09-02 | 2017-09-04 | All
Code the WBS | 2017-09-04 | 2017-09-04 | All
Integrate the WBS with the organisation (OBS) and discuss | 2017-09-05 | 2017-09-07 | All
Give an example of the work packages | 2017-09-07 | 2017-09-09 | All
Drafting the final report | 2017-09-09 | 2017-09-10 | PM's
Presenting the final report before 5pm | 2017-09-11 | 2017-09-11 | PM's

## Gantt chart
Task | 28-Aug | 29-Aug | 30-Aug | 31-Aug | 1-Sep | 2-Sep | 3-Sep | 4-Sep | 5-Sep | 6-Sep | 7-Sep | 8-Sep | 9-Sep | 10-Sep | 11-Sep
Composing of the project plan
Defining the scope
Identify and agree on main deliverables
Present individual WBS structures and discuss
Code the WBS
Integrate the WBS with the organisation (OBS) and discuss
Give an example of the work packages
Drafting the final report
Presenting the final report before 5pm